## Cover
Risk Register
Marc Seale, Chief Executive & Registrar
Report to Council 26 March 2009

## Risk Contents
Health Professions Council Risk Register
March 2009 Risk Assessment
| Contents | Page
| Contents page | 2
| HPC Risk Matrix | 3
| Top HPC risks | 4
| Strategic risks | 5
| Operations risks | 6
| Communications risks | 7
| Corporate Governance risks | 8
| Information Technology risks | 9
| Partners risks | 10
| Education risks | 11
| Project Management risks | 12
| Quality Management risks | 13
| Registration risks | 14
| HR risks | 15
| Legal risks | 16
| Fitness to Practise risks | 17
| Policy & Standards risks | 18
| Finance risks | 19 a & b
| Pensions risks | 21
| Data Security risks | 22
| Continuing Professional Development (CPD) risks | 23
| Glossary and Abbreviations | 24

## HPC Risk Matrix
HPC RISK MATRIX
| Catastrophic | 5 | 10 | 15 | 20 | 25
5
| Significant | 4 | 8 | 12 | 16 | 20
4
| Moderate | 3 | 6 | 9 | 12 | 15
IMPACT | 3
| Minor | 2 | 4 | 6 | 8 | 10
2
| Insignificant | 1 | 2 | 3 | 4 | 5
1
|  | Negligible | Rare | Unlikely | Possible | Probable
|  | 1 | 2 | 3 | 4 | 5
LIKELIHOOD
[5 empty] | Key | >11 | High Risk: Urgent action required
[6 empty] | 6 - 10 | Medium Risk: Some action required
[6 empty] | <5 | Low Risk: ongoing monitoring required

## Top HPC Risks
THE HEALTH PROFESSIONS COUNCIL
Top Risks
Description |  | Risk owner (primary person responsible for assessing and managing the ongoing risk) | Mitigation I | Status | Mitigation II | Status | Mitigation III | Status | RISK SCORE | COMMENTS
2.7 | Interuption to electricity supply | Facilities Manager | Relocate to other buildings on site |  | If site wide longer than 24 hours invoke DR Plan |  |  |  | High
13.3 | Tribunal exceptional costs, FTP, Registrations and CPD Appeals | FTP Director | Quality of legal advice | O | Quality of operational processes | O | Legal insurance cover for lawyer costs (rather than tribunals) costing between £125k and £250k | O | High | High

## Strategic Risks
THE HEALTH PROFESSIONS COUNCIL
RISK ASSESSMENT March 2009
Strategic
Ref | Category | Ref # | Description | Risk owner (primary person responsible for assessing and managing the ongoing risk) | Impact before mitigations February 2009 | Likelihood before mitigations February 2009 | Risk Score = Impact x Likelihood | Mitigation I | Status | Mitigation II | Status | Mitigation III | Status | RISK score after Mitigation February 2009 | RISK score after Mitigation September 2008
1 | Strategic | 1.1 | HPC fails to deliver Order in Council (OIC) | Council | 5 | 1 | 5 | Delivery of HPC Strategy | O | Publication of Annual Report | TBC | - | - | Low | Low
Links to 7.1-7.4, 18.1, 8.1-8.3, 10.4, 10.5, 11.4, 15.9
|  | 1.2 | Unexpected change in UK legislation | Chief Executive | 5 | 2 | 10 | Relationship with Government depts | O | Lobbying | O | - | - | Low | Low
Links to 2.2, 15.14
|  | 1.3 | Incompatible OIC and EU legislation | Chief Executive | 1 | 3 | 3 | Monitoring of EU directives e.g. Professional Qualifications Directive | O | Membership of Alliance of UK Health Regulators on Europe (lobby group) | O | - | - | Low | Low
|  | 1.4 | CHRE conflict | Chief Executive | 5 | 1 | 5 | HPC President and Chief Executive relationship with CHRE | O | Communications | O | - | - | Low | Low

## Operations
THE HEALTH PROFESSIONS COUNCIL
RISK ASSESSMENT March 2009
Operations
Ref | Category | Ref # | Description | Risk owner (primary person responsible for assessing and managing the ongoing risk) | Impact before mitigations February 2009 | Likelihood before mitigations February 2009 | Risk Score = Impact x Likelihood | Mitigation I | Status | Mitigation II | Status | Mitigation III | Status | RISK score after Mitigation February 2009 | RISK score after Mitigation September 2008
2 | Operations | 2.1 | Inability to occupy premises or use interior equipment | Facilities Manager | 4 | 2 | 8 | Invoke Disaster Recovery/Business Continuity plan | O | Commercial combined insurance cover (fire, contents, terrorism etc) | O | - | - | Low | Low
|  | 2.2 | Rapid increase in registrant numbers | Chief Executive and Director of Operations | 3 | 5 | 15 | Scaleable IT systems/registration | O | 22-26 Stannary St fit out. | O | Influence the rate at which new professions are regulated | - | Low | Low
Links to 1.2
|  | 2.3 | Unacceptable service standards | Director of Operations | 5 | 4 | 20 | ISO 9001 Registration, process maps, well documented procedures & BSI audits | C | Hire temporary staff to clear service backlogs | O | Market research surveys to prioritise service offerings | - | Low | Low
Links to 9.1, 10.4
|  | 2.4 | Postal or telephone disruption | Facilities Manager | 4 | 4 | 16 | Website, newsletter & messages | O | Invoke Disaster Recovery Plan | O | Collection of >80% income fees by DD | - | Low | Low
|  | 2.5 | General shutdown of transport systems | Facilities Manager | 4 | 5 | 20 | Contact staff via Disaster Recovery Plan process | O | Make arrangements for staff to work at home if possible | - | - | - | Low | Low
|  | 2.6 | Inability to accommodate HPC employees | Facilities Manager | 4 | 3 | 12 | Temporary premises rented | O | Phase 2 22-26 Stannary St fit out. | C | Ongoing Space planning | - | Low | Low
Links to 5.2
|  | 2.7 | Interuption to electricity supply | Facilirties Manager | 4 | 4 | 16 | Relocate to other buildings on site |  | If site wide longer than 24 hours invoke DR Plan |  |  |  | High
|  | 2.8 | Interuptiojn to gas supply | Facilities Manager | 1 | 2 | 2 | Temporary heaters to impacted areas | [5 empty] | Low
|  | 2.9 | Interuption to water supply | Facilities Manager | 2 | 2 | 4 | Reduce consumption |  | Temporarily reduce headcount to align with legislation |  | Invoke DR plan |  | Low

## Communications
THE HEALTH PROFESSIONS COUNCIL
RISK ASSESSMENT March 2009
Communications
Ref | Category | Ref # | Description | Risk owner (primary person responsible for assessing and managing the ongoing risk) | Impact before mitigations February 2009 | Likelihood before mitigations February 2009 | Risk Score = Impact x Likelihood | Mitigation I | Status | Mitigation II | Status | Mitigation III | Status | RISK score after Mitigation February 2009 | RISK score after Mitigation September 2008
3 | Communications | 3.1 | Failure to inform public Article 3 (13) | Director of Comms | 5 | 1 | 5 | Delivery of communications strategy | O | AGM, Biennial awareness survey | TBC | - | - | Low | Low
|  | 3.2 | Loss of support from the professional bodies | Director of Comms | 4 | 1 | 4 | Delivery of HPC Strategy | O | Delivery of communications strategy | O | Regular Listening Events held | - | Low | Low
|  | 3.3 | Inability to inform stakeholders following crisis | Director of Comms | 4 | 1 | 4 | Invoke Disaster Recovery Plan | C | Mailing address details kept as current as possible in Netregulate | - | - | - | Low | Low

## Corporate Governance
THE HEALTH PROFESSIONS COUNCIL
RISK ASSESSMENT March 2009
Corporate Governance
Ref | Category | Ref # | Description | Risk owner (primary person responsible for assessing and managing the ongoing risk) | Impact before mitigations February 2009 | Likelihood before mitigations February 2009 | Risk Score = Impact x Likelihood | Mitigation I | Status | Mitigation II | Status | Mitigation III | Status | RISK score after Mitigation February 2009 | RISK score after Mitigation September 2008
4 | Corporate Governance | 4.1 | Council inability to make decisions | Secretary to Council | 3 | 1 | 3 | Regular meetings, agendas and clear lines of accountability between Council and committees | C | Well researched and drafted decision papers at meetings | - | Attendance by external professionals as required | - | Low | Low
Links to 4.4
|  | 4.2 | Council members conflict of interest | President | 4 | 4 | 16 | Disclosure of members' interests to the Secretariat and ongoing Council & committee agenda item | C | Disclosure of conflict of interest in the Annual Report & on the HPC website | C | Member induction and training | O | Low | Low
|  | 4.3 | Poor decision-making eg conflicting advice or conflicting advice and decisions | President | 4 | 1 | 4 | Well-researched & drafted decision papers, Clear lines of accountability and scheme of delegation |  | President's involvement in the appointments process for lay members, induction and relevant training |  | Attendance by external professionals, as required. |  | Low | Low
|  | 4.4 | Failure to meet Council/Committee quorums | Secretary to Council | 4 | 4 | 16 | Clear communication of expectations of Council members' duties upfront | O | Adequate processes notifying Council & committee members of forthcoming meetings | C | Committee secretaries and chairmen advised that inquorate meetings must not proceed | - | Low | Low
Links to 4.1
|  | 4.5 | Members' poor performance | President | 4 | 1 | 4 | President's annual appraisal of Council members | O | Training & support at Away Days and Inductions | - | Removal under Sch 1, Para 9(1)(f) of the HPO 2001 | - | Low | Low
|  | 4.6 | Poor performance by the President | Council | 5 | 1 | 5 | Standing Orders | O | Power to remove the President under Sch 1, Article 12(1) C of the HPO 2001 | C | - | O | Low | Low
|  | 4.7 | Poor performance by Chief Executive | President | 5 | 1 | 5 | Performance reviews and regular "one to ones" with the President |  | Contract of Employment |  | - |  | Low | Low
|  | 4.8 | Improper financial incentives offered to Council members/employees | President and Chief Executive | 4 | 2 | 8 | Gifts policy | O | Council member code of conduct | O | Induction training re:adherence to Nolan principles | - | Low | Low
|  | 4.9 | Health & Safety of Council members | Secretary to Council | 4 | 2 | 8 | Personal Injury and Travel insurance |  | Restricted access to the building site (22/26 Stannary St) |  | Road safety policy (for vehicle drivers) with training to follow |  | Low | Low
Links to 6.3, 11.5
|  | 4.10 | Member recruitment problem (with the requisite skills) | President | 4 | 2 | 8 | Skills audit. Preparation of a detailed role description for restructured Council and communications strategy for potential applicants |  | Use of the Appointments Commission to advertise and recruit new members |  | Use of the Office of Public Appointments for advice (on recruitment of the requisite skills) |  | Low | Low
Links to 6.1, 11.13
|  | 4.11 | Expense claim abuse by members | Secretary to Council | 4 | 2 | 8 | Members Code of Conduct (public office) |  | Clear and comprehensive policies posted on the Council member Extranet and made clear during induction |  | Budget holder review and authorisation procedures |  | Low | Low
|  | 4.12 | Operationalise Section 60 legislation | Council | 5 | 2 | 10 | Scheme of delegation |  | MIS |  | EMT & CDT |  | Low

## Information Technology
THE HEALTH PROFESSIONS COUNCIL
RISK ASSESSMENT March 2009
Information Technology
Ref | Category | Ref # | Description | Risk owner (primary person responsible for assessing and managing the ongoing risk) | Impact before mitigations February 2009 | Likelihood before mitigations February 2009 | Risk Score = Impact x Likelihood | Mitigation I | Status | Mitigation II | Status | Mitigation III | Status | RISK score after Mitigation February 2009 | RISK score after Mitigation September 2008
5 | IT | 5.1 | Software Virus damage | Director of IT | 4 | 4 | 16 | Firewalls and anti-virus SW checks run | O | Adherence to IT policy, procedures and training | O | Regular externally run security tests and probes | O | Low | Low
Links to 2.3, 10.2
|  | 5.2 | Technology obsolescence, (HW or SW) | Director of IT | 2 | 2 | 4 | Accurate asset records and technology refresh strategy | O | Employ mainstream technology with recognised support and maintenance agreements | O | Annually review IT technology strategy | - | Low | Low
Links to 2.6, 10.2
|  | 5.3 | IT fraud or error | Director of IT | 3 | 3 | 9 | Adequate access control procedures maintained. System audit trails. | C | Regular, automatic password changes. External reviews. Daily backups. | O | Regular externally run security tests and probes | O | Low | Low
Links to 10.2 and 17.1

## Partners
THE HEALTH PROFESSIONS COUNCIL
RISK ASSESSMENT March 2009
Partners
Ref | Category | Ref # | Description | Risk owner (primary person responsible for assessing and managing the ongoing risk) | Impact before mitigations February 2009 | Likelihood before mitigations February 2009 | Risk Score = Impact x Likelihood | Mitigation I | Status | Mitigation II | Status | Mitigation III | Status | RISK score after Mitigation February 2009 | RISK score after Mitigation September 2008
6 | Partners | 6.1 | Inability to recruit and/or retain suitable Partners | Partner Manager | 4 | 4 | 16 | Sound recruitment strategy. Training | O | HR Strategy: Appropriate compensation package in place. | O | Regular appraisal system | - | Low | Low
Links to 4.10, 11.3, 7.3, 18.1
|  | 6.2 | Incorrect interpretation of law and/or SI's resulting in CHRE review | Director of FTP & Director of Educations | 5 | 2 | 10 | Training | O | Legal Assessors advice availability | O | Regular appraisal system | - | Low | Low
|  | 6.3 | Health & Safety of Partners | Partner Manager | 4 | 2 | 8 | Personal Injury and Travel insurance. Liability Insurance |  | Road Safety policy (for vehicle drivers) with training to follow |  | Restricted access to the building site (22/26 Stannary St) |  | Low | Low
Links to 4.9, 11.5
|  | 6.4 | Partners poor performance | Director of FTP, Director of Education, Head of Registration, Partner Manager | 4 | 4 | 16 | Regular appraisal system |  | Training |  |  |  | Low

## Education
THE HEALTH PROFESSIONS COUNCIL
RISK ASSESSMENT March 2009
Education
Ref | Category | Ref # | Description | Risk owner (primary person responsible for assessing and managing the ongoing risk) | Impact before mitigations February 2009 | Likelihood before mitigations February 2009 | Risk Score = Impact x Likelihood | Mitigation I | Status | Mitigation II | Status | Mitigation III | Status | RISK score after Mitigation February 2009 | RISK score after Mitigation September 2008
7 | Education | 7.1 | Non-detection of low education providers standards | Director of Education | 4 | 2 | 8 | Annual Approvals & Monitoring processes | O | Complaints about an approved programme process | - | - | - | Low | Low
Links to 1.1
|  | 7.2 | Education providers refusing visits or not submitting data | Director of Education | 3 | 1 | 3 | Legal powers (HPO 2001) | C | Delivery of Education Dpt supporting activities (e.g. publications, website and presentations) | - | - | - | Low | Low
Links to 1.1
|  | 7.3 | Inability to manage Education Provider (EP) visits | Director of Education | 4 | 2 | 8 | Adequate resourcing, training and visit scheduling | O | Approvals & monitoring processes |  | Temporary staff hire to backfill or clear work backlogs | - | Low | Low
Links to 1.1, 6.1, 11.2 & 11.3
|  | 7.4 | Loss of support from Education Provider | Chief Executive | 5 | 1 | 5 | Delivery of Education strategy (e.g. supporting activities such as publications, website and presentations) | TBC | Partnerships with Visitors and professional groups. | - | - | - | Low | Low
Links to 1.1, 14.2

## Project Management
THE HEALTH PROFESSIONS COUNCIL
RISK ASSESSMENT March 2009
Project Management
Ref | Category | Ref # | Description | Risk owner (primary person responsible for assessing and managing the ongoing risk) | Impact before mitigations February 2009 | Likelihood before mitigations February 2009 | Risk Score = Impact x Likelihood | Mitigation I | Status | Mitigation II | Status | Mitigation III | Status | RISK score after Mitigation February 2009 | RISK score after Mitigation September 2008
8 | Project Management | 8.1 | Fee change processes not operational by April 2009 | Director of Finance | 5 | 3 | 15 | Project progress monitored by EMT |  | Apply HPC's project management methodology |  | Maintain regular informal contact with Privy Council staff throughout all stages of the project |  | Low | Low
Links to 1.1, 15.3
|  | 8.2 | Failure to regulate a new profession or a post-registration qualification as stipulated by legislation | Director of Operations Project Portfolio Manager Head of Registrations, Director of Policy & Standards | 5 | 1 | 5 | Project progress monitored by EMT |  | Apply HPC's project management methodology |  | Maintain regular informal contact with Privy Council staff throughout all stages of the project |  | Low | Low
Links to 1.1, 15.3
|  | 8.3 | Legal challenge to equality and diversity scheme | Equality and diversity project lead | 4 | 2 | 8 | Appropriate legal and professional advice sought in scheme development |  | Consultation with external organisations |  | Oversight by project team and EMT |  | Low | Low
|  | 8.4 | HPC added to organisations which are legally required to publish a scheme but no scheme is published | Equality and diversity project lead | 4 | 1 | 4 | Equality and diversity project plan |  | Scheme publication by December 2007 |  | - |  | Low | Low
|  | 8.5 | Stannary St project - Phase Two | Facilities Manager | 3 | 1 | 3 | Detailed planning, design and quantity surveying of costs |  | Project progress monitored by EMT |  | Apply HPC's project management methodology |  | Low | Low
|  | 86 | Online Renewals Project | Director of Operations, Project Portfolio Manager | 4 | 4 | 16 | Engagement of experts in usability, scalability and security |  | Project progress monitored by EMT |  | Apply HPC's project management methodology |  | Low | Low
|  | 8.7 | Practitioner Psychologists on-boarding | Director of Operations, Project Portfolio Manager | 5 | 3 | 15 | Project progress monitored by EMT |  | Apply HPC's project management methodology |  |  |  | Low | Low
|  | 8.8 | Bichard Project | Director of Fitness to Practise, Project Portfolio Manager | 5 | 2 | 10 | Project progress monitored by EMT |  | Apply HPC's project management methodology |  |  |  | Low | Low

## Quality Management
THE HEALTH PROFESSIONS COUNCIL
RISK ASSESSMENT March 2009
Quality Management
Ref | Category | Ref # | Description | Risk owner (primary person responsible for assessing and managing the ongoing risk) | Impact before mitigations February 2009 | Likelihood before mitigations February 2009 | Risk Score = Impact x Likelihood | Mitigation I | Status | Mitigation II | Status | Mitigation III | Status | RISK score after Mitigation February 2009 | RISK score after Mitigation September 2008
9 | Quality Management | 9.1 | Loss of ISO 9001:2000 Certification (becomes 9001:2008 in 2009) | Director of Operations, Head of Business Improvement | 4 | 3 | 12 | Regular & internal audits |  | QMS standards applied across HPC |  | Management buy - in |  | Low | Low
Links to 2.3, 10.3

## Registration
THE HEALTH PROFESSIONS COUNCIL
RISK ASSESSMENT March 2009
Registrations
Ref | Category | Ref # | Description | Risk owner (primary person responsible for assessing and managing the ongoing risk) | Impact before mitigations February 2009 | Likelihood before mitigations February 2009 | Risk Score = Impact x Likelihood | Mitigation I | Status | Mitigation II | Status | Mitigation III | Status | RISK score after Mitigation February 2009 | RISK score after Mitigation September 2008
10 | Registration | 10.1 | Customer service failures | Director of Operations, Head of Registration | 5 | 5 | 25 | Accurate manning level forecasts |  | Adequate manpower resourcing & training |  | Supporting automation infrastructure eg call centre systems, LISA system enhancements, registration re-structure |  | Low | Low
Links to 11.1, 11.2
|  | 10.2 | NetRegulate Registration system failure | Director of IT | 5 | 3 | 15 | Effective backup and recovery procedures | O | Third party maintenance and support contract | O | Disaster recovery tests | O | Low | Low
Links to 5.1-5.3 and 17.1
|  | 10.3 | Inability to detect fraudulent applications | Director of Operations, Head of Registration | 5 | 2 | 10 | Financial audits, system audit trails | O | Policy and procedures supported by internal quality audits & specialized external Risk Management guidance | O | Regular, automatic password changes | - | Low | Low
Links to 9.1, 17.1 and 17.2
|  | 10.4 | Backlogs of registration and GP applns | Director of Operations, Head of Registration | 4 | 3 | 12 | Adequate staffing levels maintained to clear backlogs, based on accurate demand-forecasting | O | Process streamlining | O | - | - | Low | Low
Links to 1.1
|  | 10.5 | Mistake in the Registration process leading to liability for compensation to Registrant or Applicant | Director of Operations, Head of Registration | 5 | 2 | 10 | Financial audits, system audit trails |  | Professional indemnity insurance. Excess £2.5K. Limit £1M. (Doesn't cover misappropriation of funds) |  | Policy and procedures supported by ISO quality audits and process controls/checks |  | Low | Low

## HR
THE HEALTH PROFESSIONS COUNCIL
RISK ASSESSMENT March 2009
HR
Ref | Category | Ref # | Description | Risk owner (primary person responsible for assessing and managing the ongoing risk) | Impact before mitigations February 2009 | Likelihood before mitigations February 2009 | Risk Score = Impact x Likelihood | Mitigation I | Status | Mitigation II | Status | Mitigation III | Status | RISK score after Mitigation February 2009 | RISK score after Mitigation September 2008
11 | HR | 11.1 | Loss of key HPC employees (person cover risk) | President, Chief Executive and EMT | 4 | 4 | 16 | Committee chairmen cover for President loss, President and EMT cover for CE loss until interim appointment made | TBC | Cross training (partial or full) and process documentation | O | Chief Executive succession plan held by HR Director. Succession planning generally. | TBC | Low | Low
|  | 11.2 | High turnover of employees | HR Director | 3 | 2 | 6 | Remuneration and HR strategy | C | Regular performance reviews | O | Exit interview analysis | - | Low | Low
Links to 11.3
|  | 11.3 | Inability to recruit suitable employees | HR Director | 2 | 2 | 4 | HR Strategy and adequate resourcing of the HR dept | O | Careful specification of recruitment adverts and interview panel selection | O | Hire skilled temporary staff in the interim | - | Low | Low
Links to 4.10, 6.1, 11.2, 11.8
|  | 11.4 | Lack of technical and managerial skills to delivery the strategy | Chief Executive | 4 | 3 | 12 | HR strategy and goals and objectives (buy in the skills v staff upskilling on the job v training) | O | Training needs analysis & training delivery. | TBC | Some projects or work initiatives delayed or outsourced | O | Low | Low
Links to 1.1
|  | 11.5 | Health & Safety of employees | Chief Executive | 5 | 4 | 20 | Health & Safety Training, policies and procedures | C | H&S Assessments (Lawrence, Webster Forrest). | O | Personal Injury & Travel insurance | - | Low | Low
Links to 4.9, 6.3
|  | 11.6 | High sick leave levels | EMT | 2 | 3 | 6 | Adequate staff (volume and type) including hiring temporary staff | O | Return to work interviews and sick leave monitoring | O | Regular progess reviews | - | Low | Low
|  | 11.7 | Employee and ex-employee litigation | HR Director | 4 | 3 | 12 | Regular one on one sessions between manager and employee and regular performance reviews. | C | HR legislation and HR disciplinary policies | O | Compromise agreements | - | Low | Low
|  | 11.8 | Employer/employee inappropriate behaviour | HR Director | 4 | 4 | 16 | Whistle blowing policy | C | Other HR policy and procedures | C | Employee Assistance programme | - | Low | Low
Links to 11.3
|  | 11.9 | Non Compliance with Employment legislation | HR Director | 5 | 2 | 10 | HR Strategy |  | Obtain legislation updates and legal advice |  | HR policies and Manager training |  | Low | Low

## Legal
THE HEALTH PROFESSIONS COUNCIL
RISK ASSESSMENT March 2009
Legal
Ref | Category | Ref # | Description | Risk owner (primary person responsible for assessing and managing the ongoing risk) | Impact before mitigations February 2009 | Likelihood before mitigations February 2009 | Risk Score = Impact x Likelihood | Mitigation I | Status | Mitigation II | Status | Mitigation III | Status | RISK score after Mitigation February 2009 | RISK score after Mitigation September 2008
12 | Legal | 12.1 | Judicial review of Rules, Standards & Guidance | Chief Executive | 5 | 3 | 15 | Consultation. Stds determined by PLG's. Agreement by Council. | O | Appropriate legal advice sought | O | - | - | Medium | Medium
Links to 1.2

## Fitness to Practise
THE HEALTH PROFESSIONS COUNCIL
RISK ASSESSMENT March 2009
Fitness to Practise
Ref | Category | Ref # | Description | Risk owner (primary person responsible for assessing and managing the ongoing risk) | Impact before mitigations February 2009 | Likelihood before mitigations February 2009 | Risk Score = Impact x Likelihood | Mitigation I | Status | Mitigation II | Status | Mitigation III | Status | RISK score after Mitigation February 2009 | RISK score after Mitigation September 2008
13 | Fitness to Practise | 13.1 | Legal cost over-runs | FTP Director | 4 | 4 | 16 | Processes and strict arrangements with law firm suppliers | O | Professional Indemnity Insurance | C | Good process management for arranging hearings | - | Low | Low
Links to 13.4, 15.2
|  | 13.2 | Legal challenge to HPC operations | Chief Executive | 4 | 4 | 16 | Legal advice and ISO | O | Communications | O | - | - | Low | Low
|  | 13.3 | Tribunal exceptional costs, FTP, Registrations and CPD Appeals | FTP Director | 5 | 5 | 25 | Quality of legal advice | O | Quality of operational processes | O | Legal insurance cover for lawyer costs (rather than tribunals) costing between £125k and £250k | O | High | High
|  | 13.4 | Rapid increase in the number of tribunals and resultant legal costs | FTP Director | 3 | 3 | 9 | Accurate and realistic budgeting | O | Resource planning | O | - | - | Low | Low
Links to 13.1
|  | 13.5 | Witness non-attendance | FTP Director | 4 | 2 | 8 | Witness summons | TBC | Witness support programme | O | - | - | Low | Low
|  | 13.6 | Employee/Partner physical assault by Hearing attendees | FTP Director | 5 | 5 | 25 | Advice sought from the Police |  | Adequate facilities security |  | Periodic use of security contractors and other steps |  | Low | Low
|  | 13.7 | Registration Appeals | FTP Director & Director of Operations, Head of Registrations | 3 | 5 | 15 | Training and selection of Registration Assessors, so reasoned decisions are generated | O | Effective processes and criteria for arranging hearings and cases | O | - | - | Low | Low

## Policy & Standards
THE HEALTH PROFESSIONS COUNCIL
RISK ASSESSMENT March 2009
Policy & Standards
Ref | Category | Ref # | Description | Risk owner (primary person responsible for assessing and managing the ongoing risk) | Impact before mitigations February 2009 | Likelihood before mitigations February 2009 | Risk Score = Impact x Likelihood | Mitigation I | Status | Mitigation II | Status | Mitigation III | Status | RISK score after Mitigation February 2009 | RISK score after Mitigation September 2008
14 | Policy & Standards | 14.1 | Incorrect process followed to establish stds/guidance/policy eg no relevant Council decision | Policy & Stds Director | 4 | 1 | 4 | Legal advice sought on processes |  | Appropriately experienced and trained members of Policy team. |  | Quality mgt system & processes |  | Low | Low
|  | 14.2 | Inappropriate stds/guidance published eg stds are set at inappropriate level, are too confusing or are conflicting | Council/committees | 4 | 1 | 4 | Use of professional liaison groups, and Council and committees including members with appropriate expertise |  | Appropriately experienced and trained members of Policy team. |  | Consultation with stakeholders & legal advice sought |  | Low | Low
|  | 14.3 | Changing/evolving legal advice rendering previous work inappropriate | Policy & Stds Director | 4 | 2 | 8 | Use of well-qualified legal professionals. Regular reviews. |  | Legal advice obtained in writing. |  | Appropriately experienced and trained members of Policy team and others eg HR. |  | Low | Low
|  | 14.4 | Inadequate preparation for a change in legislation (Health Professions Order, or other legislation affecting HPC) | Policy & Stds Director, Director of Ops | 3 | 1 | 3 | Policy team and others remaining up to date re: forthcoming developments, via contacts, consultations, etc. |  | Project planning process and teams |  | Legal advice sought |  | Low | Low

## Finance
THE HEALTH PROFESSIONS COUNCIL
RISK ASSESSMENT March 2009
Finance
Ref | Category | Ref # | Description | Risk owner (primary person responsible for assessing and managing the ongoing risk) | Impact before mitigations February 2009 | Likelihood before mitigations February 2009 | Risk Score = Impact x Likelihood | Mitigation I | Status | Mitigation II | Status | Mitigation III | Status | RISK score after Mitigation February 2009 | RISK score after Mitigation September 2008
15 | Finance | 15.1 | Insufficient cash to meet commitments | Finance Director | 5 | 1 | 5 | Maintain an appropriate level of cash reserves for ongoing cashflow planning. Effective collections process (80% of registrants pay by DD) and applicant payment process (by credit card). | O | Annual and Five Year Plan forecasting of income (volumes & fees) and costs to ensure adherence to Reserves Policy. Fee rises as required. | O | Monthly forecasts/reviews | O | Low | Low | Refer Cash flow forecast
Links to 15.5, 15.6, 15.17, 16.1, 16.2, 16.3
|  | 15.2 | Unexpected rise in operating expenses | EMT | 3 | 1 | 3 | Finance & Resources Committee review of the Monthly variances year to date. Regular budget holder reviews held. Budget holder accountability. | C | Budgetary control clarity around permanent and timing (reversing) differences. Correct treatment of prepayments. | O | Out turn forecasts and review of remaining annual spend | O | Low | Low | Forecast Outturn indicates …
Link to 13.1
|  | 15.3 | Large Capital Project Cost Over-runs | EMT | 4 | 2 | 8 | Finance & Resources Committee review of the project spendng variances to date |  | Effective project specification, management and project progress reporting (financial and non financial) |  | Guidelines on project spending. Project exception reports promptly presented to EMT for review |  | Low | Low
Links to 8.1-8.4
|  | 15.4 | Loss in value of investment fund portfolio | Finance Director | 3 | 5 | 15 | Adherence to Investments and Reserves policies. Long run investment view. | C | Professional funds management involving diversification (by asset class, market, sector) and "lower risk side of neutral" investments | O | Relatively small balances held in the investment portfolio (£1.4M), compared to money market (£5M) and property investments held (£3M) | O | Low | Low
Links to 15.17
|  | 15.5 | Inability to pay creditors | Finance Director | 5 | 2 | 10 | Effective payment process management | C | Adequate cash-flow forecasting | C | Monthly Aged Creditors review | - | Low | Low
Links to 15.1
|  | 15.6 | Inability to collect from debtors | Finance Director | 5 | 2 | 10 | Collection via Direct Debit for >80% of fees income | C | Registrant debtors policy compliance. | - | Request new DD details from Registrants when informed by the bank that the Registrant's DD was rejected. Periodic reviews and actioning of Misc Debtors. | - | Low | Low
Links to 15.1
|  | 15.7 | Registrant Credit Card record fraud/theft | Finance Director | 3 | 1 | 3 | Daily credit card payment reconciliation's in Finance dept - Streamline to Netregulate and Bank records. | Tight procedures to retrieve sensitive paper records from archive, rationalise records kept and retain sensitive current year records with security tagging and in compliance with cr card record storage stds. | Tight procedures to retrieve sensitive paper records from archive, rationalise records kept and retain sensitive current year records with security tagging and in compliance with cr card record storage stds. |  | - |  | Low | Low
Links to 5.3
|  | 15.8 | Receipt of fee income as per collection schedule | Finance Director | 3 | 3 | 9 | Netregulate processes & controls in place (charging & receipts) |  | Monthly revenue reconciliation's between Netregulate and SAGE |  | - | - | Low | Low
|  | 15.9 | Mismatch between Council goals & approved financial budgets | Chief Executive | 4 | 2 | 8 | Adequate quantification of the budgetary implications of proposed new initiatives | C | Close and regular communication between the Executive, Council and its Committees. | O | Spending prioritisation criteria | - | Low | Low
Links to 1.1
|  | 15.10 | Unauthorised payments to organisations | Finance Director | 5 | 2 | 10 | Purchase Order approval compliance | O | Signatory list maintenance | C | Approved and one-off supplier processes |  | Low | Low
Links to 5.3
|  | 15.11 | Unauthorised payments to personnel | Finance Director | 5 | 3 | 15 | Expense claim processes | O | Signatory list reviews | C | Professional Indemnity & fraud insurance | - | Low | Low
Links to 5.3
|  | 15.12 | Unauthorised removal of assets (custody issue) | Facilities Manager | 5 | 2 | 10 | IT asset labeling & asset logging (issuance to employees) | C | Fixed Asset register itemising assets. Job exit procedures (to recover HPC laptops etc) | C | Computer insurance | - | Low | Low
|  | 15.13 | Mis-signing of cheques (forgery) | Finance Director | 4 | 3 | 12 | Regular reviews of cheque signatories against invoices paid by cheque. Photocopies of one off supplier cheques held. | O | Monthly bank reconciliations | C | Minimial use of manual chqs. Two signatories required on all cheques. | - | Low | Low
Links to 5.3
|  | 15.14 | Non compliance with FReM reporting | Finance Director | 3 | 1 | 3 | Periodic reviews of HM Treasury and NAO information updates. Technical updates from CA firms. Clarifications sought, as required. |  | Employee training |  | - |  | Low | Low
Links to 1.2
|  | 15.15 | Qualified opinion received by the Auditors on the Statutory Financial Statements | Finance Director | 5 | 1 | 5 | Internal control compliance and actioning of audit findings. |  | FReM compliance & timely market valuations eg investments, land and buildings |  | Reliable financial systems. Income, Expense & Balance Sheet Reconciliation's. Matching Sage TB to Mgt Accs & Mgt Accs to Statutory Financial Statements |  | Low | Low
|  | 15.16 | Late submission of the Annual Report, beyond sector standards | Secretary to Council | 3 | 1 | 3 | Upfront agreement on the Year End and Annual Report reporting process dates |  | Process management |  | - |  | Low | Low | YE Process in place
Links to 15.1
|  | 15.17 | Professional Fund Manager insolvency | Finance Director | 3 | 1 | 3 | Client monies (HPC) contractually separated from fund manager own holdings. |  | Periodic credit rating checks of fund manager firms used |  |  |  | Low | Low
HMRC website periodic reviews. Employee training (CPD hours)
|  | 15.18 | PAYE/NI compliance | Finance Director | 5 | 2 | 10 | Professional tax advice sought, including status of CCM's and partners |  | Payroll process management. Tax provisions made. PAYE Settlement Agreement sought (via Baker Tilly). Signed disclosure forms (Categories) |  | HMRC website periodic reviews. Employee training (CPD hours) |  | Low | Low
|  | 15.19 | Corporate Tax compliance | Finance Director | 4 | 1 | 4 | Professional tax advice sought e.g. Corporate Tax Return preparation and filing. |  | Tax provisions made |  | - |  | Low | Low
|  | 15.20 | Money market provider insolvency | Finance Director | 5 | 4 | 20 | Money market funds spread across at least two UK money market institutions, independently owned with at least an AA minus credit rating |  | Periodic credit rating checks of money market providers used eg Standard & Poors & Fitch rating monitoring. |  | - |  | Low | Low
|  | 15.21 | Financial distress of suppliers | Finance Director | 4 | 4 | 16 | Financial monitoring of key suppliers via Dun & Bradstreet |  | Escrow agreements |  | Alternative suppliers |  | Medium | Low
Page 19 b

## Pensions
THE HEALTH PROFESSIONS COUNCIL
RISK ASSESSMENT March 2009
Pensions
Ref | Category | Ref # | Description | Risk owner (primary person responsible for assessing and managing the ongoing risk) | Impact before mitigations February 2009 | Likelihood before mitigations February 2009 | Risk Score = Impact x Likelihood | Mitigation I | Status | Mitigation II | Status | Mitigation III | Status | RISK score after Mitigation February 2009 | RISK score after Mitigation September 2008
16 | Pensions | 16.1 | Under-funded pension liabilities (CPSM Retirement Benefits Scheme*) | Finance Director | 2 | 3 | 6 | Benefits secured by insurance policies issued by the Scottish Life Assurance (SLA) | C | Periodic review of the actuarial valuation of assets of the fund to cover pension liabilities. | O | Specialist pensions legal advice sought as required |  | Low | Low
Links to 15.1, 15.5
|  | 16.2 | Section 75 (Pensions Act 1995) liability for employer share of Flexiplan pension scheme deficit | Finance Director | 4 | 2 | 8 | Notional membership by six scheme members to avoid triggering s75 liability before scheme closure |  | Specialist pensions legal advice sought |  | - |  | Low | Low
Links to 15.1, 15.5
|  | 16.3 | Capita Flexiplan funding liability resulting from scheme valuation deficit | Finance Director | 4 | 4 | 16 | Monitor actions of the Employers' Consultative Group in working with the Professional Trustee to wind up the Flexiplan scheme. |  | Periodic review of the actuarial valuation of the fund (whether pension assets cover pension liabilities). |  | Specialist pensions legal advice sought as required |  | Low | Low

## Data Security
THE HEALTH PROFESSIONS COUNCIL
RISK ASSESSMENT March 2009
Data Security
Ref | Category | Ref # | Description | Risk owner (primary person responsible for assessing and managing the ongoing risk) | Impact before mitigations February 2009 | Likelihood before mitigations February 2009 | Risk Score = Impact x Likelihood | Mitigation I | Status | Mitigation II | Status | Mitigation III | Status | RISK score after Mitigation February 2009 | RISK score after Mitigation September 2008
17 | Data Security | 17.1 | Electronic record Data Security | Director of IT | 5 | 3 | 15 | Employment contract includes Data Protection Agreement |  | Adequate access control procedures maintained. System audit trails. |  | Laptop security encryption and VPN access. |  | Low | Low
Links to 5.3
|  | 17.2 | Paper record Data Security | Head of Business Improvement | 5 | 3 | 15 | Use of locked document destruction bins in each dept. Use of shredder machines for confidential record destruction in some depts e.g. Finance. |  | Data Protection agreements signed by the relevant suppliers. Dept files stored onsite in locked cabinets. |  | Regarding Reg Appln forms processing, employment contract includes Data Protection Agreement |  | Low | Medium (Reg Assessor registered mail still to arrange)
Links to 15.7
|  | 17.3 | Data held by third parties | Director of Ops and Director of IT | 5 | 3 | 15 | Data Protection/Controller agreements signed by the relevant suppliers. Use of electronic firewalls by suppliers. |  | Use of locked tape archive boxes and sign out procedures. |  | Digital Steps Ltd (Netregulate developer) access Netregulate via a secure VPN and password security. Only sample set of data held by DSL. Print UK password encryption. Peladon access using remote access tool. Electoral Reform Society data is password protected |  | Low | Medium (Servicepoint tamper proof boxes still to arrange)
|  | 17.4 | Data received from third parties | Director of Ops, and Director of FTP | 5 | 2 | 10 | Read only, password protected access by a restricted no of FTP employees to electronic KN data. |  | Registrant payments taken in compliance with Payment Card Industry (PCI) Security standards ie with quarterly PCI testing. |  | Ensure third party data providers e.g. professional bodies provide the data password protected/encrypted/door to door courier/registered mail/sign in sign out as appropriate. |  | Low | Low

## CPD
THE HEALTH PROFESSIONS COUNCIL
RISK ASSESSMENT March 2009
Continuing Professional Development
Ref | Category | Ref # | Description | Risk owner (primary person responsible for assessing and managing the ongoing risk) | Impact before mitigations February 2009 | Likelihood before mitigations February 2009 | Risk Score = Impact x Likelihood | Mitigation I | Status | Mitigation II | Status | Mitigation III | Status | RISK score after Mitigation February 2009 | RISK score after Mitigation September 2008
18 | CPD | 18.1 (7.5) | CPD processes not effective | Director of Operations, Head of Registrations | 4 | 2 | 8 | Well documented processes |  | Appropriately trained members of the registrations team |  | Monitor and regulator feedback to the Education & Training Committee |  | Low | Low
Links to 1.1

## Glossary and Abbreviations
Glossary & Abbreviations
Term | Meaning
AGM | Annual General Meeting
CDT | Cross Directorate Team (formerly HPC's Middle Management Group)
CHRE | Council for Healthcare Regulatory Excellence
CPD | Continuing Professional Development
EEA | European Economic Area, = European Economic Union, plus Norway, Iceland, plus for our purposes Switzerland
EMT | HPC's Executive Management Team
EU | European Economic Union (formerly known as the "Common Market")
FReM | Financial Reporting Manual
FTP | Fitness to Practise
GP | Grandparenting
HPO | Health Professions Order
HR | Human Resources
HW | Abbreviation for computer hardware
Impact | The result of a particular event, threat or opportunity occuring. Scored between 1 least effect on HPC and 5 maximum effect on HPC.
ISO | International Standards Organisation (the global governing body for the Quality standards used by HPC)
ISO 9001:2000 | The Quality Management Standard used by HPC, shortly being migrated to the latest version ISO9001:2008
IT | Information Technology
Likelihood | Used to mean Probability of the event or issue occurring within the next 12 months
MIS | Management Information System
NetRegulate | The bespoke computer application used to manage the application, registration and renewal processes, and publish the online register
OIC | Order in Council
Onboarding | The process of bringing a new profession into statuatory regulation from HPC's viewpoint
OPS | Operations
PLG | Professional Liason Group
Print UK | A supplier of printing and insertion/mailing services to HPC
Probability | Likelihood, chance of occurring. Not the "mathematical" probability. Scored between 1 least likely and 5 most likely to occur within the next year.
QMS | Quality Management System, used to record and publish HPC's agreed management processes
Risk | An uncertain event/s that could occur and have an impact on the achievement of objectives
Risk Score | Likelihood x Impact or Probability x Significance
Significance | Broadly similar to Impact
SSFS | Scheme Specific Funding Standard, a set of standards relating to pensions services
STDS | Standards
SW | Abbreviation for computer software
VPN | Virtual Private Network, a method of securely accessing computer systems via the public internet